## Planning
| Project Start Date: | 2024-09-03 | [5 empty] | 2024-09-10 |  |  |  | 2024-10-08 |  |  |  |  | 2024-11-12 |  |  |  | 2024-12-10
| Project Name: | REGISTRATION PORTAL |  |  |  |  | week starting | WK 1 | WK2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17
[8 empty] | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24
# | Activity | Team | Start Date | End Date | Days | Status | % Done
1 | Planning & Requirements
1.1 | Project Kickoff | FAAN & TecBlu | 2024-09-25 | 2024-12-31 | 97 | Complete | 50%
1.2 | Requirement Gathering | FAAN & TecBlu | 2024-09-11 | 2024-10-18 | 37 | Complete | 75%
1.3 | Requirement Analysis and Approval | FAAN & TecBlu | 2024-09-18 | 2024-11-08 | 51 | Complete | 20%
2 | Design & Prototyping
2.1 | User Interface (UI) Design | TecBlu | 2024-09-03 | 2024-11-08 | 66 | In Progress | 70%
2.2 | User Experience (UX) Design | TecBlu | 2024-09-03 | 2024-11-08 | 66 | In Progress | 85%
2.3 | Prototype Review and Approval | FAAN & TecBlu | 2024-09-03 | 2024-10-20 | 47 | Complete | 100%
3 | Development
3.1 | Frontend Development | TecBlu | 2024-10-09 | 2024-10-18 | 9 | Complete | 100%
3.2 | Backend Development | TecBlu | 2024-09-05 | 2024-10-12 | 37 | Complete | 100%
3.3 | Database Setup & Integration | TecBlu | 2024-09-06 | 2024-09-09 | 3 | Complete | 100%
3.4 | API Development and Integration | TecBlu | 2024-10-05 | 2024-11-10 | 36 | Complete | 100%
4 | Testing & QA
4.1 | System Testing | TecBlu | 2024-10-15 | 2024-11-08 | 24 | In Progress | 70%
4.2 | Quality Assurance (QA) | FAAN & TecBlu | 2024-10-15 | 2024-11-08 | 24 | In Progress | 60%
4.3 | Bug Fixing and Refinement | TecBlu | 2024-10-29 | 2024-11-08 | 10 | In Progress | 60%
5 | User Acceptance Testing
5.1 | User Acceptance Testing (UAT) | FAAN & TecBlu | 2024-09-27 | 2024-11-08 | 42 | In Progress | 80%
5.2 | UAT Feedback and Final Adjustments | FAAN | 2024-10-27 | 2024-11-08 | 12 | In Progress | 70%
6 | Deployment
6.1 | Final Deployment | TecBlu & FAAN | 2024-10-15 | 2024-12-31 | 77 | Awaiting Review | 10%
7 | Post-Deployment Support
7.1 | Post-Deployment Support & Monitoring | TecBlu | 2024-10-09 | 2024-12-08 | 60 | Not Started | 50%

## Report
| Project Start Date: | 2024-09-03 | [5 empty] | 2024-09-10 |  |  |  | 2024-10-08 |  |  |  |  | 2024-11-12 |  |  |  | 2024-12-10
| Project Name: | REGISTRATION PORTAL |  |  |  |  | week starting | WK 1 | WK2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17
[8 empty] | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-10 | 2024-12-17 | 2024-12-24
# | Activity | Team | Start Date | End Date | Days | Status | % Done
1 | Planning & Requirements
1.1 | Project Kickoff | FAAN & TecBlu | 2024-09-03 | 2024-12-31 | 119 | Complete | 50% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1.2 | Requirement Gathering | FAAN & TecBlu | 2024-09-11 | 2024-10-18 | 37 | Complete | 75% | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
1.3 | Requirement Analysis and Approval | FAAN & TecBlu | 2024-09-18 | 2024-11-08 | 51 | Complete | 20% | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 | Design & Prototyping
2.1 | User Interface (UI) Design | TecBlu | 2024-09-03 | 2024-11-08 | 66 | In Progress | 70% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2.2 | User Experience (UX) Design | TecBlu | 2024-09-03 | 2024-11-08 | 66 | In Progress | 85% | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2.3 | Prototype Review and Approval | FAAN & TecBlu | 2024-09-17 | 2024-10-20 | 33 | Complete | 100% | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 | Development
3.1 | Frontend Development | TecBlu | 2024-10-09 | 2024-10-30 | 21 | Complete | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3.2 | Backend Development | TecBlu | 2024-09-05 | 2024-10-12 | 37 | Complete | 100% | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3.3 | Database Setup & Integration | TecBlu | 2024-09-06 | 2024-09-09 | 3 | Complete | 100% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3.4 | API Development and Integration | TecBlu | 2024-09-05 | 2024-10-10 | 35 | Complete | 100% | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 | Testing & QA
4.1 | System Testing | TecBlu | 2024-10-15 | 2024-11-08 | 24 | In Progress | 70% | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4.2 | Quality Assurance (QA) | FAAN & TecBlu | 2024-10-15 | 2024-11-08 | 24 | In Progress | 60% | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4.3 | Bug Fixing and Refinement | TecBlu | 2024-10-29 | 2024-11-08 | 10 | In Progress | 60% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 | User Acceptance Testing
5.1 | User Acceptance Testing (UAT) | FAAN & TecBlu | 2024-09-27 | 2024-11-08 | 42 | In Progress | 80% | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5.2 | UAT Feedback and Final Adjustments | FAAN | 2024-10-27 | 2024-11-08 | 12 | In Progress | 70% | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 | Deployment
6.1 | Final Deployment | TecBlu & FAAN | 2024-10-15 | 2024-12-31 | 77 | Awaiting Review | 10% | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 | Post-Deployment Support
7.1 | Post-Deployment Support & Monitoring | TecBlu | 2024-10-09 | 2024-12-08 | 60 | Complete | 50% | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE